## Sheet1
Priority | Action | What does this look like? | Update | Achieved by
Create opportunities for tenants to influence the service in a real and meaningful way | To create and develop new opportunities for Tenant Engagement | We will create a list of the different ways in which you can be involved. | January 2025 - We are finalising the opportunities at present. | End of February 2025
| Advertise and promote the opportunities for Tenant Engagement | We will: Include information within our annual report Upload the list of opportunities onto our website Publicise on social media Promote the opportunities at any face to face event | January 2025 - we will publicise these opportunities once they have been finalised. | March 2025 and on-going
| Prioritise the opportunities for engagement based on the level of interest expressed by tenants | Once we have responses from you as to where you would like to be involved, we will start arranging these, beginning with the activities where you have expressed the most interest | January 2025 - To be reviewed once responses received from tenants | End of April 2025 and ongoing
| Offer support and training required to those who would like to engage | When setting up the activities, we will look at the areas where we can provide training to help you with the role and will also provide ongoing support to anyone interested in taking part | Janaury 2025 - we will begin this once we set up the activities/know who would like to be involved and the areas we will cover | End of December 2025
To ensure that communication is delivered and received in ways that ensures all tenants voices can be heard | Carry out a review of systems for ensuring: Resident interactions are logged, tracked and acted upon, and are fit for purpose and We identify any gaps to ensure that we are consistently completing the communication loop, whatever the activity | We will review our processes to ensure that there are clear records of contact (ie repairs report, safety concern or information required from a resident group) We will also ensure that tenants and staff are clear about timescales for responses and interactions We will ensure that we keep you updated | January 2025 - not yet started | End of December 2025 and ongoing
| Explore and develop methods of communication by social media | We will look at how we can communicate by social media where this is a preferred option for our tenants | January 2025 - not yet started | End of December 2025
| Review the methods of communication into ESC Housing to ensure ease of use for all Website Contact numbers (including how these are publicised) MyHome Emails | We will look at how you can contact us and ensure this is well publicised and straightforward | January 2025 - we have started to look at these areas | End of December 2025 and ongoing
| Analyse collected data to identify specific needs and preferences to enable 2 way communication within all areas of our community | We will carry out a Tenant Census during 2025 to ensure that we have up-to-date contact details for you and confirmation of how you would prefer that we contact you. During this, we will also ask you whether you have any specific needs so that we can take these into account. | January 2025 - we are currently looking at what information we need so that we can best support and contact you along with how we are going to gather this information/use it effectively. | End of December 2025 and ongoing
Transparent and Open Performance | Provide an annual report to tenants to include the information from the Tenant Satisfaction Measures and communicate any actions to be taken to make any improvements | We will be sending you an annual report with this information | January 2025 - the report is currently being finalised and we are hoping to send this to you in early March 2025 | Early March 2025
| Develop and support a tenant-led process to challenge the service and make recommendations for improvement in relation to the Tenant Satsifaction Measures and review our performance against the Housing Ombudsman Complaint Handling Code with our involved tenants | Within our annual report, we will be letting you know how our tenants have rated us in relation to the Tenant Satisfaction Measures and Complaint Handling. As noted above, we want to set up a Tenant Scrutiny Group/Tenant Board. This will allow us to work with tenants to look at our processes and services and hold us to account for the services we provide. We will take on board the opinions of the group(s) to make improvements | January 2025 - once we have interest in a Tenant Scrutiny Group/Board, we will look at the areas decided by the groups | End of December 2025 and ongoing
To build respectful and trusting relationships between tenants and staff | Promote the benefits of tenant engagement within the Housing Service and ensure this is included within any changes to service/service reviews | It is important that we have your input in any changes we make and service reviews. We will do this by our tenant engagement opportunities mentioned above. We will ensure that we communicate the benefits of this within the Housing Services Team so that you are included. | January 2025 - We have already started to promote the benefits of tenant engagement within Housing Services and will look to expland on this | End of December 2025 and ongoing
| Incorporate tenant engagement into the induction | To ensure that new members of our team are aware of the benefits of tenant engagement, we will include this within our induction programme | January 2025 - We have not yet started this but will look to do so during the second quarter of 2025 | End of December 2025 and ongoing