## Sheet1
Priority | Action | What does this look like? | Progress Update | Links | Target completion date
Create opportunities for tenants to influence the service in a real and meaningful way | Create and develop ongoing opportunities for Tenant Engagement | We will create a list of the different ways tenants can be in helping to shape the services that effect them. We will update this on a regular basis, as new opportunities become avaliable. | Ways to be involved have been created, click on the link to read more | ESCTenantEngagement | End of February 2025 Complete and ongoing
| Advertise and promote opportunities for Tenant Engagement | We will: Include information within our annual report Upload the list of opportunities onto our website Publicise on social media Promote the opportunities at any face to face event | March 2025 - all tenants received a letter directing them to our Housing Services Annual Report which contained details of how tenants can help us to shape our services. -website updated with the engagement opportunities -details of the engagement opportunities provided at Drop-ins and Estate Action Days - on-going -promotion of tenant engagement within ESC internal communication to encourage engagement from all team members April 2025 onwards - Promotion on Social Media mid April and on a monthly basis |  | March 2025 Complete and ongoing
| Prioritise opportunities for engagement based on the level of interest expressed by tenants | Once we have responses from tenants as to where they would like to be involved, we will start arranging these activities, commencing with those where the most interest has been expressed | April 2025 -we are going to review/consider different ways to encourage tenants to participate -details of tenant engagement added to MyHome front page |  | End of April 2025 and ongoing
| Offer support and training required, as appropriate, to those who would like to engage | When setting up activities, we will look at the areas where we can provide training to help with the role, providing ongoing support to those interested in taking part | January 2025 - we will begin this once we set up the activities/know who would like to be involved and the areas we will cover |  | End of December 2025
Ensure that communication is delivered and received in ways that all tenants voices can be heard | Carry out a review of systems to ensure: Tenant interactions are recorded and resolved as appropriate and We identify and close any gaps to ensure we are comminicating effectively with our tenants at every opportunity | We will review our processes ensuring they: Show clear records of contact (i.e repairs, safeguarding or information required from a resident group) Tenants and staff are clear about timescales for responses and interactions and that we keep you updated | April 2025 - not yet started |  | End of December 2025 and ongoing
| Explore and develop methods of communication via social media | We will look at how we can improve communication by social media where this is a preferred method for our tenants | January 2025 - not yet started April 2025 - we have increased our use of social media through our ESC page as a way of communicating with tenants who use this platform |  | End of December 2025
| Review the methods of communication into East Suffolk Council's Housing team, including: Website Contact numbers (including how these are publicised) MyHome Emails | We will review how tenants can contact us, ensuring this is straightforward and well publicised | January 2025 - we have started to look at these areas April 2025 - this is continuing |  | End of December 2025 and ongoing
| Analyse data to identify specific needs and preferences within all areas of our community | We will carry out a Tenant Census throughout 2025, updating contact details and household information. During this, we will also ask you whether you have any specific needs so that we can take these into account. | April 2025 - we are arranging for an external company called Acuity to carry out the tenant census and this will be underway shortly |  | End of December 2025 and ongoing
Transparent and Open Performance | Provide an annual report to tenants, including information from Tenant Satisfaction Measures, and communicate any actions to be taken to make any improvements | We will be sending you an annual report with this information | March 2025 - the report was completed and we wrote to all tenants advising how they can read our report or obtain a copy in a preferred format. This report covered the calendar year of 2023 - 2024 and can be found through the following link To align with the financial year, we will produce future annual reports during the summer of each year with effect from 2025. | Annual Report 2023 - 2024 | Early March 2025 Completed and on-going
| Develop and support a tenant-led process to challenge the service and make recommendations for improvement in relation to Tenant Satsifaction Measures. Review our performance against the Housing Ombudsman's Complaint Handling Code. | Publish an annual report advising how our tenants have rated us against the tenant satisfaction measures and complaint handling code. As noted above, we want to set up a Tenant Scrutiny Group/Tenant Board. This will allow us to work with tenants to look at our processes and services and hold us to account for the services we provide. We will take on board the opinions of the group(s) to make improvements | April 2025- interest in a Tenant Scrutiny Group/Board has not been successful, we will review how we can encourage our tenants to take part |  | End of December 2025 and ongoing
To build respectful and trusting relationships between tenants and staff | Promote the benefits of tenant engagement within the Housing portfolio, ensuring this is included within any changes to services | It is important that we have tenants input in any changes we make. We will do this through tenant engagement opportunities. We will ensure that we communicate the benefits of this within the Housing portfolio. | April 2025 - promotion of tenant engagement within ESC internal communication to encourage engagement from all team members |  | End of December 2025 and ongoing
| Incorporate tenant engagement into the new staff induction | We will include a presentation for new members of our team in the induction programme so they are aware of the benefits of tenant engagement | April 2025 - we are considering how we can best include this with all team members |  | End of December 2025 and ongoing